## Daily Scrum
Sprint | Unique ID | User Stories | Particulars (Today's work- Date to be mentioned) | Assignee | Reporter (Scrum Master) | Present / Absent | Status | Resolution | Fix Version/s | Product Backlog
Sprint-1 | 1 | DB & Config Setup | Reviewed backlog item for DB & Config Setup; planning starts tomorrow | P Sheetal Reddy | P Sheetal Reddy | Present | To Do | Unresolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 2 | Seed Data | Attended sprint planning; Seed Data assigned and estimated | Khandelwal Yash Ajay | P Sheetal Reddy | Present | To Do | Unresolved | v1.0 | Insert demo user, accounts, transactions, messages, payees via seed.sql
Sprint-1 | 3 | Global Layout | Researched approach for Global Layout; no blockers | Kondapaneni Nikitha | P Sheetal Reddy | Present | To Do | Unresolved | v1.0 | Build header.php and footer.php with responsive dark-navy/gold theme
Sprint-1 | 4 | CSS & JS | Attended sprint planning; CSS & JS assigned and estimated | Allam Mahitha | P Sheetal Reddy | Present | To Do | Unresolved | v1.0 | Create style.css (CSS variables, cards, forms, accordions) and main.js
Sprint-1 | 5 | User Registration | Attended sprint planning; User Registration assigned and estimated | Vijay Raj Shekhar | P Sheetal Reddy | Present | To Do | Unresolved | v1.0 | Implement register.php with validation: name, email, mobile, DOB, password strength
Sprint-1 | 6 | DB & Config Setup | Finished DB & Config Setup; conducted peer review and merged to main | P Sheetal Reddy | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 7 | DB & Config Setup | Wrapped up DB & Config Setup; unit tested and verified on localhost | Khandelwal Yash Ajay | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 8 | DB & Config Setup | Wrapped up DB & Config Setup; unit tested and verified on localhost | Kondapaneni Nikitha | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 9 | DB & Config Setup | Delivered DB & Config Setup; demo given to Scrum Master | Allam Mahitha | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 10 | DB & Config Setup | Finished DB & Config Setup; conducted peer review and merged to main | Vijay Raj Shekhar | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 11 | DB & Config Setup | Delivered DB & Config Setup; demo given to Scrum Master | P Sheetal Reddy | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 12 | DB & Config Setup | Absent – DB & Config Setup work paused for the day | Khandelwal Yash Ajay | P Sheetal Reddy | Absent | In Progress | Unresolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 13 | DB & Config Setup | Completed DB & Config Setup; pushed to feature branch and raised PR | Kondapaneni Nikitha | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 14 | DB & Config Setup | Delivered DB & Config Setup; demo given to Scrum Master | Allam Mahitha | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 15 | DB & Config Setup | Delivered DB & Config Setup; demo given to Scrum Master | Vijay Raj Shekhar | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 16 | DB & Config Setup | Finished DB & Config Setup; conducted peer review and merged to main | P Sheetal Reddy | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 17 | DB & Config Setup | Finished DB & Config Setup; conducted peer review and merged to main | Khandelwal Yash Ajay | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 18 | DB & Config Setup | Completed DB & Config Setup; pushed to feature branch and raised PR | Kondapaneni Nikitha | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 19 | DB & Config Setup | Delivered DB & Config Setup; demo given to Scrum Master | Allam Mahitha | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 20 | DB & Config Setup | Absent – DB & Config Setup work paused for the day | Vijay Raj Shekhar | P Sheetal Reddy | Absent | In Progress | Unresolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 21 | DB & Config Setup | Completed DB & Config Setup; pushed to feature branch and raised PR | P Sheetal Reddy | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 22 | DB & Config Setup | Completed DB & Config Setup; pushed to feature branch and raised PR | Khandelwal Yash Ajay | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 23 | DB & Config Setup | Completed DB & Config Setup; pushed to feature branch and raised PR | Kondapaneni Nikitha | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint-1 | 24 | DB & Config Setup | Wrapped up DB & Config Setup; unit tested and verified on localhost | Allam Mahitha | P Sheetal Reddy | Present | Done | Resolved | v1.0 | Set up MySQL schema (12 tables), PDO singleton, session helpers and utility functions
Sprint | Unique ID | User Stories | Particulars (Today's work- Date to be mentioned) | Assignee | Reporter (Scrum Master) | Present / Absent | Status | Resolution | Fix Version/s | Product Backlog
Sprint-2 | 121 | Transaction History UI | Reviewed backlog item for Transaction History UI; planning starts tomorrow | P Sheetal Reddy | P Sheetal Reddy | Present | To Do | Unresolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 122 | Last 10 Filter | Reviewed backlog item for Last 10 Filter; planning starts tomorrow | Khandelwal Yash Ajay | P Sheetal Reddy | Present | To Do | Unresolved | v2.0 | Implement 'Last 10 Transactions' filter and results table with expandable rows
Sprint-2 | 123 | Last Month Filter | Reviewed backlog item for Last Month Filter; planning starts tomorrow | Kondapaneni Nikitha | P Sheetal Reddy | Present | To Do | Unresolved | v2.0 | Implement 'Last 1 Month' date filter for transaction history
Sprint-2 | 124 | Date Range Filter | Reviewed backlog item for Date Range Filter; planning starts tomorrow | Allam Mahitha | P Sheetal Reddy | Present | To Do | Unresolved | v2.0 | Implement custom date-range filter with from/to date pickers
Sprint-2 | 125 | Dispute Flow | Researched approach for Dispute Flow; no blockers | Vijay Raj Shekhar | P Sheetal Reddy | Present | To Do | Unresolved | v2.0 | Add 'Raise Dispute' form for Credit Card transactions in expandable row
Sprint-2 | 126 | Transaction History UI | Wrapped up Transaction History UI; unit tested and verified on localhost | P Sheetal Reddy | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 127 | Transaction History UI | Wrapped up Transaction History UI; unit tested and verified on localhost | Khandelwal Yash Ajay | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 128 | Transaction History UI | Wrapped up Transaction History UI; unit tested and verified on localhost | Kondapaneni Nikitha | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 129 | Transaction History UI | Completed Transaction History UI; pushed to feature branch and raised PR | Allam Mahitha | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 130 | Transaction History UI | Delivered Transaction History UI; demo given to Scrum Master | Vijay Raj Shekhar | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 131 | Transaction History UI | Completed Transaction History UI; pushed to feature branch and raised PR | P Sheetal Reddy | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 132 | Transaction History UI | Completed Transaction History UI; pushed to feature branch and raised PR | Khandelwal Yash Ajay | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 133 | Transaction History UI | Wrapped up Transaction History UI; unit tested and verified on localhost | Kondapaneni Nikitha | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 134 | Transaction History UI | Absent – Transaction History UI work paused for the day | Allam Mahitha | P Sheetal Reddy | Absent | In Progress | Unresolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 135 | Transaction History UI | Wrapped up Transaction History UI; unit tested and verified on localhost | Vijay Raj Shekhar | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 136 | Transaction History UI | Finished Transaction History UI; conducted peer review and merged to main | P Sheetal Reddy | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 137 | Transaction History UI | Wrapped up Transaction History UI; unit tested and verified on localhost | Khandelwal Yash Ajay | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 138 | Transaction History UI | Completed Transaction History UI; pushed to feature branch and raised PR | Kondapaneni Nikitha | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 139 | Transaction History UI | Completed Transaction History UI; pushed to feature branch and raised PR | Allam Mahitha | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 140 | Transaction History UI | Delivered Transaction History UI; demo given to Scrum Master | Vijay Raj Shekhar | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 141 | Transaction History UI | Finished Transaction History UI; conducted peer review and merged to main | P Sheetal Reddy | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 142 | Transaction History UI | Completed Transaction History UI; pushed to feature branch and raised PR | Khandelwal Yash Ajay | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 143 | Transaction History UI | Wrapped up Transaction History UI; unit tested and verified on localhost | Kondapaneni Nikitha | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI
Sprint-2 | 144 | Transaction History UI | Finished Transaction History UI; conducted peer review and merged to main | Allam Mahitha | P Sheetal Reddy | Present | Done | Resolved | v2.0 | Build transactions/history.php with account filter and period filter UI